## Sheet1
BETSE project timesheet

Date	Hours Worked	Total Time (hrs)	Activity	Milestone
Jan 1st 2015	9 am to 6 pm	8	Voronoi data structure: created, closed & clipped	Voronoi
Jan 2nd 2015	4 pm – 8 pm	4	Worked with Voronoi diagram to calculate cell-specific area, membrane domains and nearest	Voronoi
			neighbour matrices.
Jan 3rd 2015	9 am to 7 pm	8	Created pre-defined special plotting functions to associate a data structure with	Port
			cell polygons, membrane-domains, smoother centres grid, and nearest-neighbour connections.
Jan 4th 2015	2 pm to 10 pm	8	Fixed Voronoi clip bug + concave hull for proper boundary and cluster shape specification	Voronoi
Jan 8th 2015	2 pm to 10 pm	8	More work on comp geom module and plotting (concave hull bug fixed + new structures)	Voronoi
Jan 9th 2015	1 pm to 9 pm	8	Finished the basic comp geom module (world.py) with cell-specific vector and ecm data	Port
Jan10th 2015	9 am to 1 pm	4	Fixing and improving plots and preparing a progress report	Port
	5 pm to 9 pm	4	Fixed gap junctions, improved plots, fixed documentation	Port
Jan 11th 2015	5 pm to 9 pm	4	Data structures for computational loops	Port
Jan 15th 2015	10 am to 9 pm	8	Data structures for computational loops	Port
Jan 16th	10 am to 10 pm	10	Implementing diffusion computations & RK4 methodology	RK4 solver
Jan 17th	10 am to 10 pm	10	Implemented electrodiffusion computations on gj-connected cells and ecm segments + RK4	RK4 solver
Jan 23rd	12pm to 10 pm	8	Created basic simulation loop with NaKATPase pumps and electrodiffusion in individual cells.	Port
Jan 24th	9 am to 10 pm	8	Working on gap junctions	Port
Jan 25th	9 am to 5pm	8	Running, saving & loading initialization and simulation runs. GJ implementations in BETSE.	Port
Jan 29th	5 pm to 9 pm	4	Code clean up.	Port
Jan 30th	10 am to 2pm	4	Graph interactivity and code clean up	Port
Feb 1st	10 am to 9 pm	8	Animations and code clean up.	Port
Feb5th	2pm to 10 pm	8	Gap junctions and user interventions	Port
Feb 6th	10 am to 10 pm	10	Voltage gated sodium and potassium channels	Port
Feb 7th	10 am to 9 pm	8	Voltage gated sodium and potassium channels – matrix format and parameter optimization	Port
Feb 13th	2 to 6 pm	4	Calcium dynamics	Ca2+ features
Feb 14th	10 am to 10 pm	10	Channel and calcium dynamics	Ca2+ features
Feb 15th	10 am to 10 pm	10	Channel and calcium dynamics	Ca2+ features
Feb 16th	10 am to 10 pm	10	User plotting features and code clean up	Port
Feb 20th	10 am to 10 pm	10	Improved plotting features	Port
Feb 21st	10 am to 10 pm	10	Improved plotting features and yaml file for user configuration specifications	Port
Feb 22nd	10 am to 10 pm	10	Improved vgNa and vgK dynamics and yaml config	Port
Feb 26th	2pm to 11 pm	8	Bicarbonate buffer, HKATPase pump dynamics corrected.	H+ features