## Sheet1
BETSE project timesheet

Date	Hours Worked	Total Time (hrs)	Activity	Milestone
Jan 1st 2015	9 am to 6 pm	8	Voronoi data structure: created, closed & clipped	Voronoi
Jan 2nd 2015	4 pm – 8 pm	4	Worked with Voronoi diagram to calculate cell-specific area, membrane domains and nearest	Voronoi
			neighbour matrices.
Jan 3rd 2015	9 am to 7 pm	8	Created pre-defined special plotting functions to associate a data structure with	Port
			cell polygons, membrane-domains, smoother centres grid, and nearest-neighbour connections.
Jan 4th 2015	2 pm to 10 pm	8	Fixed Voronoi clip bug + concave hull for proper boundary and cluster shape specification	Voronoi
Jan 8th 2015	2 pm to 10 pm	8	More work on comp geom module and plotting (concave hull bug fixed + new structures)	Voronoi
Jan 9th 2015	1 pm to 9 pm	8	Finished the basic comp geom module (world.py) with cell-specific vector and ecm data	Port
Jan10th 2015	9 am to 1 pm	4	Fixing and improving plots and preparing a progress report	Port
	5 pm to 9 pm	4	Fixed gap junctions, improved plots, fixed documentation	Port
Jan 11th 2015	5 pm to 9 pm	4	Data structures for computational loops	Port
Jan 15th 2015	10 am to 9 pm	8	Data structures for computational loops	Port
Jan 16th	10 am to 10 pm	8	Implementing diffusion computations & RK4 methodology	RK4 solver
Jan 17th	10 am to 10 pm	8	Implemented electrodiffusion computations on gj-connected cells and ecm segments + RK4	RK4 solver
Jan 23rd	12pm to 10 pm	8	Created basic simulation loop with NaKATPase pumps and electrodiffusion in individual cells.	Port
Jan 24th	9 am to 10 pm	8	Working on gap junctions	Port
Jan 25th	9 am to 5pm	8	Running, saving & loading initialization and simulation runs. GJ implementations in BETSE.	Port
Jan 29th	5 pm to 9 pm	4	Code clean up.	Port
Jan 30th	10 am to 2pm	4	Graph interactivity and code clean up	Port